## Confirmed Items
# | Stories | Task | Dil | Emre | Manish | Keith | Preethi | Elli
1 | Remove 4 pack and 12 pack Vivix, remove the variants for product page on Vivix
FGIM Changes
|  | AEM (US en/es) |  |  |  | 5
|  | Remove autoship discount skus |  |  |  |  | 1
3 | Fraud Prevention for vivix
|  | FE messaging - Review page | 2
|  | Integration with Auth service | 1
|  | Setting up promo to determine orders to be sent to Decision Manager | [5 empty] | 2
|  | Setting up Exception List | [5 empty] | 2
|  | Setup Promo - Integration Testing |  | 2 |  |  |  | 4
|  | Sending IP address to CyberSource | [5 empty] | 1
|  | IP - Integration Testing |  | 3 |  |  |  | 1
|  | Error Handling from CyberSource | [5 empty] | 4
|  | Error Handling - Integration Testing |  | 3 |  |  |  | 5
|  | Setting up Promo action in MC |  | 5
|  | Sending IP to Auth service |  | 5
|  | Passing "Fraud Detection" flag to Auth service |  | 5
|  | Error Handing in MC |  | 5
| Canada Healthy Solutions wizard/kit | [5 empty] | 6
Temporarily Unavailable flag for Canada
|  | Displaying it in MC |  |  |  |  | 2
|  | Displaying it in PWS/Shaklee.com |  |  |  |  | 2
|  | Read the status flag and set it in CanadaItemMapper |  |  |  |  | 3
|  | Integration with Paul |  |  |  |  | 8
| Residential flag for US | Capturing the value from Strike Iron Validation |  |  | 5 |  |  |  | done
|  | Passing the value across all the pages in the checkout flow |  |  | 5 |  |  |  | done
|  | Send RDI flag it to SDS |  |  | 5 |  |  |  | done
|  | Send RDI flag to SDS for autoship orders |  |  | 5 |  |  |  | pending
|  | Autoship Integration testing |  |  | 5 |  |  |  | pending
|  | Storing it in Address table only if "Save for future use" is checked |  |  | 5 |  |  |  | done
|  | Fetching the RDI flag for existing addresses in the address book in shopping flow |  |  | 5 |  |  |  | done
|  | Handling NULL values for RDI flag incase of Strike Iron down |  |  | 5 |  |  |  | pending
|  | Saving RDI flag when adding an address in the Shipping Addresses section |  |  | 5 |  |  |  | pending
|  | SSOE changes to incorporate RDI flag |  |  | 5 |  |  |  | pending
|  | Mobile Integration testing |  |  | 5 |  |  |  | pending
|  | SDS Integration Testing |  |  | 5 |  |  |  | pending
| Adding Vivix Liquigel to the Rx wizard (Regular) | DB changes |  |  |  |  | 2
|  | Integration Testing |  |  |  |  | 3
| Coupon Messaging for Life Plan | FE display | 2
|  | Integration Testing | 5
|  | Learning Promo Engine | 5
|  | Setup Promo Engine environment | 5
|  | Promo Engine Rules | 5
|  | Promo Engine Unit Testing | 5
| Missing Translations |  | 6 |  | 6 |  | 6
| Promo Engine UI | Planning | 5
|  | UI | 3
|  | Integration with Datasets | 5
| Minimum char length for CC first and last name | MC Checkout/ Join/Sponsor/Guest Checkout | 5
|  | Autoship Creation | 1
|  | Hearsay | 1
|  | PWS Creation | 1
|  | LA Center Shopping | 1
|  | LA Center Sponsor | 1
| Member Center Home Page: move Home-Page 'New Tools' and 'News & Events' banner area into ConMan |  | 1
| Total hrs assigned per developer |  | 60 | 28 | 60 | 5 | 27 | 19
| Total hrs available per developer |  | 60 | 30 | 60 | 60 | 60 | 60

## Extra Items
8 | Order charge share for Canada
9 | Vivix liquigels to Rx
10 | Healthy Solutions Customization
11 | Residential Flag
12 | International Creditcards
10 | Canada - Chinese and Hmong languages
11 | Upsell for Life Plan coupons